## Sheet1
Date	Feature	Description	Estimation of time, h	Wasted time, h
9.11.19	Create a base project	Write program for stm32 which will contain necessary functions for core working.	1	1
10.11.19	LCD-Display	Write functions for working with LCD-Display	2
13.11.19	Humidity, temperature	Write functions for working with DHT11	2
16.11.19	Site	Write html code	1
17.11.19	Wi-fi module	Write code for wi-fi module and stm32 for communication between them	2
20.11.19	Light	Write functions for light control	1
23.11.19	Sound	Write functions for sounds	2
24.11.19	Emergency signalization	Write functions for emergency signalization	1
27.11.19	Ventilation	Write functions for ventilation control	1
30.11.19	Opening door	Write functions for motor control	2
31.11.19	RFID	Write functions for RFID identification	2
			17
Deadline:
9.12.19